Intel® Teach Program Getting Started Course v.2.0

Curriculum Adaptation
Updating from v.1.0 to v.2.0

Introduction

This document is designed to help you adapt and update the Intel® Teach Getting Started Course curriculum materials from version 1.0 to version 2.0. The intent of this document and (related adaptation documents) is to serve as a guide as you create your own curriculum materials, using the completed curriculum files (language: U.S. English) and provided templates as a model.

It is recommended that you refer to this document prior to and during the development of your Getting Started curriculum.

NOTE: This document only includes information about adapting and updating the Getting Started Course curriculum manuals to version 2.0. This is only intended for countries that already have the Getting Started Course v.1.0 materials adapted and complete. Should you require additional information about adapting the Intel® Education Help Guide (digital version), please see the associated Help Guide Adaptation Toolkit.

Contents of this Document:

- Introduction, Related Documents, and Contacts	Page 1

- Software Requirements	Page 2

- Adaptation Process	Page 3

- Adaptation Timeline (Recommended Model)	Page 4

Related Documents:

- Adaptation FAQ: This document provides answers to frequently asked adaptation questions.

- Complete Curriculum Files (language: U.S. English): The Production Kit CD contains complete production files for the curriculum manual (language: U.S. English). You will be adapting these files (translating and localizing) to create your country’s curriculum.

- Curriculum Changes: This document provides a bulleted list of general and specific changes made to v.1.0 to create v.2.0.

- Complete Curriculum Files (language: U.S. English) with Highlighted Changes: These files show all text changes highlighted in blue and contains comments explaining where to move selected exercises to improve the flow of the materials. Note that the files also contain yellow highlights to differentiate margin notes and icon placeholders. 
These files are available on the Production Kit CD.

Contacts:

If you have questions or need assistance with adaptation, please contact Shelley Shott (Shelley.shott@intel.com).

Software Requirements

To create your curriculum, you must meet or exceed the following software requirements:

Mandatory Software Requirements

Adobe Acrobat Reader 5.0* or above is required to: View the complete curriculum files (language: U.S. English) [PDF versions]

Neo Sans Intel font family in your country’s language (or Intel CBID approved alternative) is required to: Create your curriculum manuals

Optional Software Requirements

QuarkXPress 5.0* or higher is required to: View and modify the complete curriculum files (language: U.S. English) Note: If you are using publication software other than QuarkXPress, you will need to recreate the manual formatting in that software.

Adaptation Process When Updating to v.2.0

Pre-Production: Review (and translate if needed) all adaptation documents for the Getting Started v.2.0 curriculum. Establish your adaptation team and adaptation timeline. Purchase software for use in adaptation and production (if needed).

Step 1: Adapt (translate and localize) text highlighted in blue in all Word files of the Getting Started v.2.0 materials found in the Adaptation folder. Note: Margin notes and icon placeholders are differentiated from the other text with yellow highlights.

Step 2: Replace existing v.1.0 text with the updated v.2.0 text.

Step 3: Locate all comments within the Word files and address each one. This will involve moving exercises where indicated.

Step 4: Check and update all page references throughout the materials.

Step 5: Review and edit your completed manual.

Step 6: Send a PDF version of your final manual to Shelley Shott at Shelley.shott@intel.com for a high-level review. Make any identified changes to your manual and finalize it.

Step 7: Determine how you will print and distribute your curriculum materials to MTs and PTs. Recommended options include: Option A: Print one manual for MTs and PTs and then print the MT appendix separate (for distribution to only MTs). Option B: Print one manual for MTs (which includes the curriculum and MT Appendix) and print a separate manual for PTs (which only includes the curriculum).

Step 8: Print your final files. Refer to the Intel® Teach Curriculum Guidelines for information on print specifications and paper and binding recommendations.

Adaptation Timeline (Recommended Model)

This is a model for a recommended timeline/schedule for completing production of the Getting Started curriculum manual update from v.1.0 to v.2.0. Please adapt this timeline to suit your needs and develop your own adaptation and production timeline.

- Assumed resources: 1 full-time production person, 1 part-time editor, and 1 manager to oversee project management aspects part-time

- Acceleration options: This timeline could be shortened if additional resources are available to work on the project. Also, if your country has already adapted the Help Guide, that process step can be bypassed.

|  | Week 1 | Week 2 | Week 3 | Week 4 |
| --- | --- | --- | --- | --- |
| Pre-Production: Review (and translate, if needed) the adaptation documents Establish an adaptation team & timeline Purchase software for use in production (if needed) |  |  |  |  |
| Step 1: Adapt the text highlighted in blue. |  |  |  |  |
| Step 2: Update text, move exercises, and check page references. |  |  |  |  |
| Step 4: Review and edit your completed manual |  |  |  |  |
| Step 5: Send PDF version of the manual to Shelley Shott for review. Make any identified changes. |  |  |  |  |

NOTE: Post-production items are not on this adaptation timeline.

- Printing the materials may take three weeks or longer.

- Distribution time will vary based on the number of participants and locations involved.